Markdown

# Odoo Construction & Engineering Management Suite (CEMS)
**Software Requirements Specification (SRS) & Architecture Blueprint**
**Version:** 1.1.0 | **Target Framework:** Odoo 16/17/18 (Community & Enterprise)

---

## Table of Contents
1. [Executive Summary & Architecture Overview](#1-executive-summary--architecture-overview)
2. [Module Dependencies & Technical Matrix](#2-module-dependencies--technical-matrix)
3. [Functional Specifications & Mathematical Models](#3-functional-specifications--mathematical-models)
4. [System File & Directory Architecture](#4-system-file--directory-architecture)
5. [Security Matrix & Record Rules (RBAC)](#5-security-matrix--record-rules-rbac)
6. [Odoo Development Methodology](#6-odoo-development-methodology)
7. [Prioritized Development Roadmap](#7-prioritized-development-roadmap)

---

## 1. Executive Summary & Architecture Overview

The **Odoo Construction & Engineering Management Suite (CEMS)** is a specialized ERP extension engineered to bridge field execution with enterprise resource planning. Native Odoo modules supply backend financial, purchasing, inventory, and human resource framework capabilities, while seven custom addons deliver domain-specific construction workflows.

This architecture ensures high maintainability by strictly adhering to Odoo's inheritance framework—leaving core modules untouched while injecting construction logic via custom addons.

### 1.1 System Architecture Diagram

```text
┌─────────────────────────────────────────────────────────────────────────┐
│                    Executive Construction Dashboard                     │
│               (`construction_dashboard` - OWL Client Action)            │
└────────────────────────────────────┬────────────────────────────────────┘
                                     │
┌────────────────────────────────────┴────────────────────────────────────┐
│                           Custom Domain Addons                          │
├───────────────┬───────────────┬───────────────┬───────────┬─────────────┤
│   Engineering │   Progress    │   Logistics   │  Site HRD │   HSE & QC  │
│(`engineering`)│ (`progress`)  │ (`logistics`) │  (`hrd`)  │ (`hse`/`qc`)│
└───────┬───────┴───────┬───────┴───────┬───────┴─────┬─────┴──────┬──────┘
        │               │               │             │            │
┌───────▼───────────────▼───────────────▼─────────────▼────────────▼──────┐
│                            Native Odoo Core                             │
│        (project, stock, purchase, fleet, hr, account, analytic)         │
└─────────────────────────────────────────────────────────────────────────┘

## 2. Module Dependencies & Technical Matrix

To prevent database relation errors, modules must declare strict dependencies. Below is the technical matrix defining the relationship between custom addons and core Odoo apps.

| Functional Domain | Odoo Core Dependencies | Custom Addon Name | Key Custom/Extended Models (_name or _inherit) |
| --- | --- | --- | --- |
| 1. Engineering | documents, mail | construction_engineering | construction.drawing, construction.transmittal, construction.rfi.tech |
| 2. Progress & WBS | project, hr_timesheet | construction_progress | project.project, project.task, construction.daily.report, construction.wbs |
| 3. Site Logistics | stock, purchase, fleet | construction_logistics | construction.material.request, fleet.vehicle, stock.picking |
| 4. Site HRD | hr, hr_attendance | construction_hrd | construction.daily.labor, construction.gate.pass, hr.attendance |
| 5. HSE (Safety) | hr, construction_progress | construction_hse | construction.permit.work, construction.incident, construction.jsa |
| 6. QC (Quality) | project, construction_engineering | construction_qc | construction.inspection.request, construction.ncr, construction.punchlist |
| 7. Dashboard | All of the above | construction_dashboard | construction.kpi.view (SQL Auto-View), OWL Dashboard Component |

## 3. Functional Specifications & Mathematical Models

### 3.1 Project Construction Progress (construction_progress)

Calculates actual physical work progress across Work Breakdown Structure (WBS) hierarchies and feeds data into financial analytics.

- Task Weightage Assignment ($W_i$): Each WBS task is assigned a percentage weight relative to the total project scope. The system will enforce a validation constraint where:
$$\sum_{i=1}^{n} W_i = 100\%$$

- Physical Progress Calculation ($P_{\text{total}}$):
$$P_{\text{total}} = \sum_{i=1}^{n} (W_i \times P_i)$$
(where $P_i$ represents the actual physical completion percentage of task $i$, updated via the Daily Site Report)

- Earned Value Management (EVM) Integration:
$$\text{Earned Value (EV)} = P_{\text{total}} \times \text{Budget At Completion (BAC)}$$
$$\text{Schedule Performance Index (SPI)} = \frac{\text{Earned Value (EV)}}{\text{Planned Value (PV)}}$$

### 3.2 Site Logistics & Asset Management (construction_logistics)

Bridges the gap between field engineers and the procurement department.

- Material Requisition (MR) Lifecycle:
Draft $\rightarrow$ Submitted $\rightarrow$ Site Manager Approved $\rightarrow$ Procurement Review $\rightarrow$ PO/Transfer Created $\rightarrow$ Received at Site.

- Equipment Tracking: Extends fleet.vehicle to track Hobbs meter (engine hours) against specific project.project analytical accounts to calculate machine depreciation per project.

### 3.3 Site HRD & Geofenced Attendance (construction_hrd)

Manages site labor distribution and portal-based worker clock-ins.

- Daily Labor Report (DLR): A daily form logging headcount by trade (Carpenters, Masons, Electricians) split by Direct Hire vs. Subcontractor.

- Geofenced Selfie Attendance System:

  - Uses HTML5 navigator.geolocation and <input type="file" capture="user"> inside an Odoo Portal Controller.

  - Haversine Formula Backend Validation: The server validates the GPS payload against the Project's center point.
$$d = 2r \arcsin\left(\sqrt{\sin^2\left(\frac{\phi_2 - \phi_1}{2}\right) + \cos(\phi_1)\cos(\phi_2)\sin^2\left(\frac{\lambda_2 - \lambda_1}{2}\right)}\right)$$
Where: $d$ = Distance (meters), $r$ = Earth's radius ($6,371,000$ m), $\phi$ = Latitude, $\lambda$ = Longitude.

  - Rule: If $d > \text{geofence\_radius}$, raise Odoo ValidationError.

### 3.4 Health, Safety & Environment (construction_hse)

- Permit to Work (PTW): State-machine workflow for high-risk operations (Hot Work, Excavation, Confined Space). Requires digital signatures from HSE Officer and Site Manager before tasks can begin.

- Incident Metrics:
$$\text{LTI Frequency Rate (LTIFR)} = \left( \frac{\text{Number of LTIs} \times 1,000,000}{\text{Total Hours Worked}} \right)$$

### 3.5 Quality Control (construction_qc)

- Non-Conformance Report (NCR): Issued for defective work.

- Database Constraint Trigger: If a project.task has an active/open NCR linked to it, the system overrides the task form and disables the physical_progress field, preventing progress claims until the NCR state moves to Closed.

### 3.6 Engineering & EDMS (construction_engineering)

- Revision Trees: Tracks Rev 0, Rev 1, Rev A (As-Built).

- Transmittal Matrix: Auto-generates PDF QWeb reports for outgoing document transmittals (submittals to client/consultant).

## 4. System File & Directory Architecture

To maintain code cleanliness, developers must adhere to standard Odoo directory scaffolding. Below is the detailed structure required for the core modules.

Plaintext

custom_addons/
├── construction_progress/
│   ├── __init__.py
│   ├── __manifest__.py
│   ├── models/
│   │   ├── project_project.py        # Adds Geofence lat/long/radius
│   │   ├── project_task.py           # Adds WBS and EVM calculations
│   │   └── daily_site_report.py      # New DSR model
│   ├── views/
│   │   ├── project_views_inherit.xml # XPath injections for task forms
│   │   ├── daily_report_views.xml    # Form, Tree, and Kanban for DSR
│   │   └── menu_items.xml            # App routing
│   └── security/
│       ├── ir.model.access.csv       # Table permissions
│       └── ir_rules.xml              # Multi-project isolation rules
│
├── construction_hrd/
│   ├── controllers/
│   │   └── portal_attendance.py      # HTTP endpoints for GPS/Base64 Photo POST requests
│   ├── static/src/
│   │   ├── js/geolocation.js         # HTML5 Sensor logic
│   │   └── xml/camera_widget.xml     # Mobile UI for selfie
│   └── views/
│       └── portal_templates.xml      # Worker-facing web page
│
└── construction_dashboard/
    ├── static/src/
    │   ├── components/               # OWL Components (Odoo 16+)
    │   │   ├── dashboard.js
    │   │   ├── dashboard.xml
    │   │   └── chart_widget.js       # Chart.js / ApexCharts wrapper
    └── models/
        └── kpi_sql_view.py           # Uses `tools.drop_view_if_exists` for fast SQL aggregation

## 5. Security Matrix & Record Rules (RBAC)

Security is implemented in two layers: Model Access (ir.model.access.csv) defining what a role can do globally, and Record Rules (ir.rule) defining what specific rows they can see.

### 5.1 Access Matrix (CRUD Mapping)

| Role Name | Internal Group (res.groups) | Progress | Logistics | HSE | QC | Dashboard |
| --- | --- | --- | --- | --- | --- | --- |
| Project Director | group_cems_director | Read | Read | Read | Read | Full |
| Project Manager | group_cems_manager | Full | Approve | Approve | Approve | Project |
| Site Engineer | group_cems_engineer | Write | Create | Read | Create | Project |
| HSE Officer | group_cems_hse | Read | Read | Full | Read | HSE KPIs |
| QC Inspector | group_cems_qc | Read | Read | Read | Full | QC KPIs |
| Worker (Portal) | base.group_portal | Own Task | None | Alerts | None | None |

### 5.2 Critical Record Rules (ir.rule)

To prevent data leakage between project sites, Record Rules must be enforced:

- Site Engineer Isolation: Site Engineers can only read/write Tasks and Daily Reports where project_id matches projects they are explicitly assigned to.

  - Domain: [('project_id.user_id', '=', user.id)]

- Worker Geofence Lock: Workers can only view their own attendance records and portal profiles.

  - Domain: [('employee_id.user_id', '=', user.id)]

## 6. Odoo Development Methodology

Strict Rule: Never copy, modify, or delete standard Odoo core files.

### The Inheritance Paradigm

All customizations must use _inherit in Python and <xpath> in XML.

Python Example: Adding WBS to Tasks

Python

from odoo import models, fields

class ProjectTask(models.Model):
    _inherit = 'project.task'  # Injects fields into existing table

    wbs_code = fields.Char(string='WBS Code', index=True)
    weightage_pct = fields.Float(string='Weightage (%)')

XML Example: Injecting Fields into the UI

XML

<record id="view_task_form_cems" model="ir.ui.view">
    <field name="name">project.task.form.cems</field>
    <field name="model">project.task</field>
    <field name="inherit_id" ref="project.view_task_form2"/>
    <field name="arch" type="xml">
        <!-- Find deadline field, insert WBS right after it -->
        <xpath expr="//field[@name='date_deadline']" position="after">
            <field name="wbs_code"/>
            <field name="weightage_pct"/>
        </xpath>
    </field>
</record>

## 7. Prioritized Development Roadmap

Because ERP relationships are strictly hierarchical (e.g., you cannot request materials for a project that doesn't exist), development must follow these sequential phases.

### Phase 1: The Core Foundation (Weeks 1-3)

Target Module: construction_progress

- Define all 10 internal User Roles (res.groups) in a base security file.

- Extend project.project (Add Geofence Radius, Center Lat/Long).

- Extend project.task (Add WBS, Weightage, EVM computation logic).

- Implement Record Rules to isolate projects by Project Manager.

### Phase 2: Site Workforce & Portal (Weeks 4-5)

Target Module: construction_hrd

- Extend hr.employee to link workers to specific project.project sites.

- Develop Python Controller for Haversine Geofence validation.

- Build the Odoo Portal Web-App (HTML5 JS for Camera and GPS prompt).

### Phase 3: Field Execution & Logistics (Weeks 6-8)

Target Modules: construction_progress (Part 2) & construction_logistics

- Build construction.daily.report (DSR) model and link it to Task physical progress.

- Build construction.material.request model.

- Establish state-machine logic: auto-create stock.picking (internal transfer) upon Material Request approval.

### Phase 4: Compliance & Quality (Weeks 9-11)

Target Modules: construction_engineering, construction_hse, construction_qc

- Install base Document Management app; add construction revision statuses.

- Build PTW (Permit to Work) models with digital signature requirements.

- Build NCR (Non-Conformance) models. Key logic: Intercept write method on project.task to block progress updates if an NCR is unclosed.

### Phase 5: Executive Analytics (Weeks 12-14)

Target Module: construction_dashboard

- Write raw PostgreSQL views via Python _auto = False models to aggregate EVM, Safety, and Inventory data efficiently.

- Develop OWL (Odoo Web Library) frontend components.

- Integrate Chart.js or ApexCharts for dynamic S-Curve rendering.